## How to use
Preventive maintenance plan
How to use
1. One row per task: equipment code and name, what is done, and how many days between each execution.
2. In 'Last done' enter the date the task was last performed, and update it every time it is carried out.
3. The Status column shows overdue tasks in red and tasks due within the next 7 days in yellow.
4. Your plan defines the frequencies: the formula does not decide them, it only tracks them. To calibrate them, look at the 6:1 ratio.
Colors
Yellow: cells to fill in.
Gray: formulas, do not edit.
Method source
Types of maintenance and planning: see the articles 'Types of maintenance' and '6:1 ratio' on LKaizeN.com.ar.
The example values entered are made up to show how it works: delete them and enter your own.
Free spreadsheet from LKaizeN (LKaizeN.com.ar). Use it, adapt it and share it.

## Plan
Preventive maintenance plan
Fill in the yellow columns. The next due date, the days left and the status are calculated automatically.
Code | Equipment | Task | Frequency (days) | Owner | Last done | Next due | Days left | Status
EQ-001 | Main air compressor | Replace air filter and check levels | 90 | Shift mechanic | 2026-07-01 | 2026-09-29 | 9 | On time
EQ-002 | Outfeed conveyor belt | Lubricate bearings and check belt tension | 30 | Lubricator | 2026-08-20 | 2026-09-19 | -1 | Overdue
EQ-003 | Wash pump | Inspect mechanical seal | 60 | Shift mechanic | 2026-06-15 | 2026-08-14 | -37 | Overdue
Formulas:
Next due = IF(OR([Last done]="",[Frequency (days)]=""),"",[Last done]+[Frequency (days)])
Days left = IF([Next due]="","",[Next due]-TODAY())